# CuraLive Platform — Replit Outstanding Tasks Brief

For: Replit Development Team

      From: Manus Project Management

      Date: March 11, 2026

      Priority: CRITICAL — Production Deployment Required

      Timeline: 14 days to production readiness

## Executive Summary

Replit has successfully delivered 4,485 lines of new code implementing 5 major feature systems. The platform is 85% complete and ready for final testing, QA, and production deployment.

Current Status:

- ✅ Frontend implementation: 100% complete

- ✅ Backend routers: 100% complete

- ✅ Database schema: 100% complete

- ⚠️ Build verification: Pending

- ⚠️ Testing suite: Pending

- ⚠️ Production deployment: Pending

What's Blocking Production:

- TypeScript compilation errors (need to fix)

- Database table creation (need to run scripts)

- Test suite creation (need to write tests)

- Performance validation (need to verify)

- Production deployment (need to execute)

## Phase 1: Build Verification & Error Fixes (Days 1-2)

### Task 1.1: TypeScript Compilation Check

Objective: Verify all TypeScript compiles without errors

Steps:

# Navigate to project

cd /home/ubuntu/chorus-ai

# Run TypeScript compiler

npx tsc --noEmit

# Expected: 0 errors

# If errors found: Fix all type issues

Deliverable: Clean TypeScript compilation with 0 errors

Acceptance Criteria:

- No TypeScript errors

- No console warnings

- All imports resolve correctly

- All type definitions complete

Estimated Time: 2-4 hours

### Task 1.2: Full Build Verification

Objective: Verify production build completes successfully

Steps:

# Clean previous builds

rm -rf dist .vite node_modules/.vite

# Install dependencies

pnpm install

# Run production build

pnpm run build

# Expected: Build completes in <60 seconds with 0 errors

Deliverable: Successful production build

Acceptance Criteria:

- Build completes without errors

- Build time <60 seconds

- No warnings in build output

- dist/ folder contains all assets

- Source maps generated

Estimated Time: 1-2 hours

### Task 1.3: Vite/esbuild Configuration Validation

Objective: Verify build configuration is correct

Steps:

# Check vite.config.ts

cat vite.config.ts

# Verify:

# - publicDir correctly configured

# - build output correct

# - server configuration correct

# - resolve aliases working

Deliverable: Validated build configuration

Acceptance Criteria:

- vite.config.ts syntax correct

- All aliases resolve

- Build output path correct

- Server configuration valid

Estimated Time: 30 minutes

## Phase 2: Database Setup (Days 2-3)

### Task 2.1: Create Shadow Sessions Table

Objective: Set up shadow_sessions table for testing environment

Steps:

# Run migration script

pnpm exec tsx scripts/create-shadow-sessions-table.ts

# Verify table created

pnpm exec tsx scripts/verify-tables.ts | grep shadow_sessions

# Expected output: shadow_sessions table exists with all columns

Deliverable: shadow_sessions table created and verified

Acceptance Criteria:

- Table created successfully

- All columns present

- Indexes created

- Foreign keys configured

- Default values set

Estimated Time: 30 minutes

### Task 2.2: Create Agentic Brain Table

Objective: Set up agentic_brain_events table for AI intelligence

Steps:

# Run migration script

pnpm exec tsx scripts/create-agentic-brain-table.ts

# Verify table created

pnpm exec tsx scripts/verify-tables.ts | grep agentic_brain

# Expected output: agentic_brain_events table exists

Deliverable: agentic_brain_events table created and verified

Acceptance Criteria:

- Table created successfully

- All columns present

- Indexes created

- Foreign keys configured

Estimated Time: 30 minutes

### Task 2.3: Create Autonomous Interventions Table

Objective: Set up autonomous_interventions table for proactive alerts

Steps:

# Run migration script

pnpm exec tsx scripts/create-autonomous-interventions-table.ts

# Verify table created

pnpm exec tsx scripts/verify-tables.ts | grep autonomous_interventions

# Expected output: autonomous_interventions table exists

Deliverable: autonomous_interventions table created and verified

Acceptance Criteria:

- Table created successfully

- All columns present

- Indexes created

- Foreign keys configured

Estimated Time: 30 minutes

### Task 2.4: Create Operator Link Analytics Tables

Objective: Set up analytics tracking for operator links

Steps:

# Run migration script

pnpm exec tsx scripts/create-operator-link-analytics-tables.ts

# Verify tables created

pnpm exec tsx scripts/verify-tables.ts | grep operator_link

# Expected output: operator_link_analytics and operator_links_metadata tables exist

Deliverable: Operator link analytics tables created and verified

Acceptance Criteria:

- Both tables created successfully

- All columns present

- Indexes created

- Foreign keys configured

Estimated Time: 30 minutes

### Task 2.5: Create Tagged Metrics Table

Objective: Set up tagged_metrics table for performance tracking

Steps:

# Run migration script

pnpm exec tsx scripts/create-tagged-metrics-table.ts

# Verify table created

pnpm exec tsx scripts/verify-tables.ts | grep tagged_metrics

# Expected output: tagged_metrics table exists

Deliverable: tagged_metrics table created and verified

Acceptance Criteria:

- Table created successfully

- All columns present

- Indexes created

- Foreign keys configured

Estimated Time: 30 minutes

### Task 2.6: Seed Initial Data

Objective: Populate tables with initial test data

Steps:

# Create seed script

cat > scripts/seed-initial-data.ts << 'EOF'

// Seed data for all new tables

// Include sample records for testing

EOF

# Run seed script

pnpm exec tsx scripts/seed-initial-data.ts

# Verify data created

pnpm exec tsx scripts/verify-seed-data.ts

Deliverable: Initial test data seeded into all tables

Acceptance Criteria:

- Sample records created in each table

- Data validates against schema

- Relationships intact

- Ready for testing

Estimated Time: 1 hour

## Phase 3: Testing Suite Creation (Days 3-5)

### Task 3.1: Create Shadow Mode Router Tests

Objective: Write comprehensive tests for shadowModeRouter

Steps:

# Create test file

cat > server/routers/shadowModeRouter.test.ts << 'EOF'

import { describe, it, expect } from 'vitest';

import { shadowModeRouter } from './shadowModeRouter';

describe('shadowModeRouter', () => {

// Test all procedures

// - createShadowSession

// - getShadowSession

// - listShadowSessions

// - updateShadowSession

// - deleteShadowSession

// - recordShadowAction

// - getShadowAnalytics

});

EOF

# Run tests

pnpm test server/routers/shadowModeRouter.test.ts

Deliverable: Comprehensive test suite for Shadow Mode

Acceptance Criteria:

- All procedures tested

- 80% code coverage

- All tests passing

- Error cases handled

- Edge cases covered

Estimated Time: 2 hours

### Task 3.2: Create Agentic Brain Router Tests

Objective: Write comprehensive tests for agenticEventBrainRouter

Steps:

# Create test file

cat > server/routers/agenticEventBrainRouter.test.ts << 'EOF'

import { describe, it, expect } from 'vitest';

import { agenticEventBrainRouter } from './agenticEventBrainRouter';

describe('agenticEventBrainRouter', () => {

// Test all procedures

// - analyzeEvent

// - getEventAnalysis

// - listEventAnalyses

// - updateAnalysis

// - deleteAnalysis

// - generateInsights

});

EOF

# Run tests

pnpm test server/routers/agenticEventBrainRouter.test.ts

Deliverable: Comprehensive test suite for Agentic Brain

Acceptance Criteria:

- All procedures tested

- 80% code coverage

- All tests passing

- AI logic validated

- Error handling tested

Estimated Time: 2 hours

### Task 3.3: Create Autonomous Interventions Router Tests

Objective: Write comprehensive tests for autonomousInterventionRouter

Steps:

# Create test file

cat > server/routers/autonomousInterventionRouter.test.ts << 'EOF'

import { describe, it, expect } from 'vitest';

import { autonomousInterventionRouter } from './autonomousInterventionRouter';

describe('autonomousInterventionRouter', () => {

// Test all procedures

// - triggerIntervention

// - getIntervention

// - listInterventions

// - updateIntervention

// - resolveIntervention

// - getInterventionMetrics

});

EOF

# Run tests

pnpm test server/routers/autonomousInterventionRouter.test.ts

Deliverable: Comprehensive test suite for Autonomous Interventions

Acceptance Criteria:

- All procedures tested

- 80% code coverage

- All tests passing

- Trigger logic validated

- Resolution tracking tested

Estimated Time: 2 hours

### Task 3.4: Create Operator Links Router Tests

Objective: Write comprehensive tests for operatorLinksRouter

Steps:

# Create test file

cat > server/routers/operatorLinksRouter.test.ts << 'EOF'

import { describe, it, expect } from 'vitest';

import { operatorLinksRouter } from './operatorLinksRouter';

describe('operatorLinksRouter', () => {

// Test all procedures

// - trackLinkClick

// - getLinkAnalytics

// - getPopularLinks

// - getOperatorAnalytics

// - updateLinkMetadata

});

EOF

# Run tests

pnpm test server/routers/operatorLinksRouter.test.ts

Deliverable: Comprehensive test suite for Operator Links

Acceptance Criteria:

- All procedures tested

- 80% code coverage

- All tests passing

- Analytics tracking validated

- Link metadata tested

Estimated Time: 1.5 hours

### Task 3.5: Create Tagged Metrics Router Tests

Objective: Write comprehensive tests for taggedMetricsRouter

Steps:

# Create test file

cat > server/routers/taggedMetricsRouter.test.ts << 'EOF'

import { describe, it, expect } from 'vitest';

import { taggedMetricsRouter } from './taggedMetricsRouter';

describe('taggedMetricsRouter', () => {

// Test all procedures

// - recordMetric

// - getMetrics

// - getMetricsByTag

// - calculateMetricStats

// - getMetricTrends

});

EOF

# Run tests

pnpm test server/routers/taggedMetricsRouter.test.ts

Deliverable: Comprehensive test suite for Tagged Metrics

Acceptance Criteria:

- All procedures tested

- 80% code coverage

- All tests passing

- Calculations validated

- Trends analyzed correctly

Estimated Time: 1.5 hours

### Task 3.6: Run Full Test Suite

Objective: Execute all tests and verify coverage

Steps:

# Run all tests

pnpm test

# Generate coverage report

pnpm test -- --coverage

# Expected output:

# - All tests passing

# - Coverage >80%

# - No failing tests

Deliverable: Full test suite passing with >80% coverage

Acceptance Criteria:

- All tests passing (0 failures)

- Coverage >80%

- No console errors

- Performance acceptable (<5s total)

Estimated Time: 1 hour

## Phase 4: Performance Validation (Days 5-6)

### Task 4.1: Dashboard Load Time Testing

Objective: Verify dashboard loads in <2 seconds

Steps:

# Start dev server

pnpm dev &

# Wait for server to start

sleep 10

# Run Lighthouse audit

npx lighthouse http://localhost:3000/admin/interconnection-analytics \

--chrome-flags="--headless" \

--output-path=./lighthouse-report.html

# Check metrics:

# - First Contentful Paint: <1s

# - Largest Contentful Paint: <2s

# - Cumulative Layout Shift: <0.1

Deliverable: Lighthouse performance report

Acceptance Criteria:

- Load time <2 seconds

- Lighthouse score >90

- FCP <1 second

- LCP <2 seconds

- CLS <0.1

Estimated Time: 30 minutes

### Task 4.2: API Response Time Testing

Objective: Verify API responses in <200ms

Steps:

# Create performance test script

cat > scripts/test-api-performance.ts << 'EOF'

// Test API response times for all procedures

// Record response times

// Verify <200ms average

EOF

# Run performance tests

pnpm exec tsx scripts/test-api-performance.ts

# Expected output:

# - Average response time <200ms

# - P95 response time <500ms

# - P99 response time <1000ms

Deliverable: API performance test results

Acceptance Criteria:

- Average response <200ms

- P95 response <500ms

- P99 response <1000ms

- No timeouts

- Consistent performance

Estimated Time: 1 hour

### Task 4.3: Real-Time Latency Testing

Objective: Verify Ably real-time updates in <1 second

Steps:

# Create real-time latency test

cat > scripts/test-realtime-latency.ts << 'EOF'

// Test Ably message delivery latency

// Measure end-to-end latency

// Verify <1 second

EOF

# Run real-time tests

pnpm exec tsx scripts/test-realtime-latency.ts

# Expected output:

# - Average latency <1 second

# - P95 latency <2 seconds

# - No message loss

Deliverable: Real-time latency test results

Acceptance Criteria:

- Average latency <1 second

- P95 latency <2 seconds

- No message loss

- Consistent delivery

- Handles high volume

Estimated Time: 1 hour

### Task 4.4: Cross-Browser Testing

Objective: Verify functionality on all major browsers

Steps:

# Test on:

# - Chrome/Chromium

# - Firefox

# - Safari

# - Edge

# - Mobile browsers

# Manual testing checklist:

# - All pages load

# - All links work

# - Forms submit correctly

# - Real-time updates work

# - No console errors

Deliverable: Cross-browser compatibility report

Acceptance Criteria:

- Chrome: ✅ Pass

- Firefox: ✅ Pass

- Safari: ✅ Pass

- Edge: ✅ Pass

- Mobile: ✅ Pass

- No console errors

- All features work

Estimated Time: 2 hours

## Phase 5: Production Deployment (Days 6-7)

### Task 5.1: Production Environment Setup

Objective: Configure production environment variables

Steps:

# Set production environment variables

# In Manus Settings → Secrets:

# Database

DATABASE_URL=<production_database_url>

# Authentication

JWT_SECRET=<production_jwt_secret>

OAUTH_SERVER_URL=<oauth_url>

VITE_OAUTH_PORTAL_URL=<oauth_portal_url>

# Real-time

ABLY_API_KEY=<ably_key>

# Other required secrets

# (See MANUS_TECH_STACK.md for complete list)

Deliverable: Production environment configured

Acceptance Criteria:

- All secrets configured

- Database URL correct

- OAuth configured

- Ably key valid

- No hardcoded secrets

Estimated Time: 30 minutes

### Task 5.2: Deploy to Staging

Objective: Deploy to staging environment for final testing

Steps:

# Create staging branch

git checkout -b staging

# Deploy to staging

git push staging main

# Wait for deployment to complete

# Verify staging URL: https://staging.curalive-mdu4k2ib.manus.space

# Run smoke tests

pnpm test:smoke

# Verify all features work on staging

Deliverable: Staging deployment verified

Acceptance Criteria:

- Deployment completes successfully

- All pages load

- All links work

- Authentication works

- Real-time updates work

- No errors in logs

- Performance acceptable

Estimated Time: 1 hour

### Task 5.3: Production Deployment

Objective: Deploy to production domain

Steps:

# Merge staging to main

git checkout main

git merge staging

# Deploy to production

git push production main

# Wait for deployment to complete

# Verify production URL: https://curalive-mdu4k2ib.manus.space

# Run smoke tests

pnpm test:smoke

# Verify all features work on production

Deliverable: Production deployment verified

Acceptance Criteria:

- Deployment completes successfully

- All pages load at production URL

- All links work

- Authentication works

- Real-time updates work

- No errors in logs

- Performance acceptable

- Monitoring active

Estimated Time: 1 hour

### Task 5.4: Post-Deployment Monitoring

Objective: Monitor production for errors and performance

Steps:

# Monitor logs

tail -f .manus-logs/devserver.log

tail -f .manus-logs/browserConsole.log

tail -f .manus-logs/networkRequests.log

# Check metrics

# - Page load time

# - API response time

# - Error rate

# - User count

# Set up alerts for:

# - High error rate

# - High latency

# - Downtime

Deliverable: Production monitoring configured

Acceptance Criteria:

- Logs being collected

- Metrics being tracked

- Alerts configured

- Dashboard visible

- No critical errors

Estimated Time: 1 hour

## Phase 6: Operator Training & Documentation (Days 8-14)

### Task 6.1: Create Shadow Mode Training Guide

Objective: Document Shadow Mode for operators

Deliverable: Comprehensive training guide

Content:

- Overview of Shadow Mode

- How to create test sessions

- How to record operator actions

- How to analyze performance

- Common use cases

- Troubleshooting

Estimated Time: 2 hours

### Task 6.2: Create Agentic Brain Training Guide

Objective: Document Agentic Brain for operators

Deliverable: Comprehensive training guide

Content:

- Overview of AI intelligence

- How to trigger analysis

- How to interpret insights

- How to use recommendations

- Common use cases

- Troubleshooting

Estimated Time: 2 hours

### Task 6.3: Create Autonomous Interventions Training Guide

Objective: Document Autonomous Interventions for operators

Deliverable: Comprehensive training guide

Content:

- Overview of proactive alerts

- How to configure triggers

- How to respond to alerts

- How to resolve interventions

- Common scenarios

- Troubleshooting

Estimated Time: 2 hours

### Task 6.4: Create Operator Links Training Guide

Objective: Document Operator Links for operators

Deliverable: Comprehensive training guide

Content:

- Overview of navigation hub

- How to access each feature

- Link organization and structure

- Analytics and tracking

- Best practices

- Troubleshooting

Estimated Time: 1 hour

### Task 6.5: Create Tagged Metrics Training Guide

Objective: Document Tagged Metrics for operators

Deliverable: Comprehensive training guide

Content:

- Overview of performance tracking

- How to view metrics

- How to interpret data

- How to export reports

- Common metrics

- Troubleshooting

Estimated Time: 1.5 hours

### Task 6.6: Conduct Operator Training Sessions

Objective: Train operators on all new features

Steps:

- Schedule training sessions

- Provide access to Shadow Mode

- Walk through each feature

- Answer questions

- Collect feedback

- Provide certification

Deliverable: All operators trained and certified

Acceptance Criteria:

- 90% operator attendance

- 80% completion rate

- 4/5 satisfaction rating

- All questions answered

- Feedback collected

Estimated Time: 7 days (ongoing)

## Critical Success Checklist

### Before Production Deployment

Code Quality:

- TypeScript: 0 errors

- Build: Successful

- Tests: >80% coverage, all passing

- Linting: 0 warnings

- Performance: All targets met

Database:

- All 5 tables created

- All migrations successful

- Initial data seeded

- Backups configured

- Monitoring set up

Security:

- All secrets configured

- Authentication working

- Authorization enforced

- Data validation in place

- No console errors

Documentation:

- API docs complete

- Database schema documented

- Training guides created

- Deployment procedures documented

- Troubleshooting guide created

Testing:

- Unit tests: >80% coverage

- Integration tests: Passing

- Performance tests: Targets met

- Cross-browser: All browsers passing

- Smoke tests: Passing

## Timeline & Milestones

| Phase | Duration | Start | End | Status |
| --- | --- | --- | --- | --- |
| Build Verification | 2 days | Day 1 | Day 2 | 🔴 Pending |
| Database Setup | 2 days | Day 2 | Day 3 | 🔴 Pending |
| Testing Suite | 3 days | Day 3 | Day 5 | 🔴 Pending |
| Performance | 2 days | Day 5 | Day 6 | 🔴 Pending |
| Deployment | 2 days | Day 6 | Day 7 | 🔴 Pending |
| Training | 7 days | Day 8 | Day 14 | 🔴 Pending |
| Total | 14 days | Today | 2 weeks | Ready to start |

## Immediate Action Items (Start Today)

Priority 1 (Must Do Today):

- Run TypeScript compiler and identify errors

- Run production build and verify success

- Review build output for issues

Priority 2 (Complete by Tomorrow):

- Fix any TypeScript errors

- Run all 5 database creation scripts

- Verify all tables created

Priority 3 (Complete by End of Week):

- Create and run all test suites

- Run performance tests

- Deploy to staging

- Run smoke tests

## Support & Resources

Documentation:

- MANUS_TECH_STACK.md — Architecture and tech stack

- MANUS_DEPLOYMENT_STATUS.md — Current deployment status

- replit.md — Replit-specific setup guide

- OPERATOR_LINKS_DEPLOYMENT_BRIEF.md — Operator links details

Files & Scripts:

- scripts/create-*.ts — Database creation scripts

- server/routers/*.ts — Backend routers

- client/src/pages/*.tsx — Frontend pages

- vitest.config.ts — Test configuration

Contact:

- Technical questions: Contact Manus team

- Deployment issues: Contact DevOps team

- Training questions: Contact Training team

## Success Metrics

| Metric | Target | Current | Status |
| --- | --- | --- | --- |
| TypeScript Errors | 0 | ❓ | 🔴 |
| Build Success | 100% | ❓ | 🔴 |
| Test Coverage | >80% | ❓ | 🔴 |
| Tests Passing | 100% | ❓ | 🔴 |
| Load Time | <2s | ❓ | 🔴 |
| API Response | <200ms | ❓ | 🔴 |
| Uptime | 99.9% | ❓ | 🔴 |
| User Satisfaction | >4.5/5 | ❓ | 🔴 |

## Next Steps

- Review this brief with your team

- Assign tasks to team members

- Start Phase 1 (Build Verification) immediately

- Report progress daily

- Escalate blockers immediately

Document Status: Ready for Replit Implementation

      Priority Level: CRITICAL

      Timeline: 14 days to production

      Last Updated: March 11, 2026

## Questions?

If you have any questions about these tasks, please contact the Manus project team immediately. We're here to support your success.

Let's ship this! 🚀